## Dashboard
REELNEST ¦ BUILD 19 — DEVELOPMENT STATUS
Source-code readiness across 282 original tasks • Not an end-to-end acceptance certificate
Source status | Task count | % of 282
Locally implemented | 57 | 20.21%
Partially implemented | 97 | 34.4%
Prepared, not executed | 43 | 15.25%
Externally blocked | 17 | 6.028%
Not started / no evidence found | 68 | 24.11%
TOTAL | 282 | 100%
ACCEPTANCE STATUS: 0/282 tasks have complete live/production acceptance evidence.
All task details are filterable in the “All 282 Tasks” tab. Workstream counts are formula-based.

## All 282 Tasks
ID | Workstream | Requirement | Priority 117 | Status | Accepted? | Evidence level | Indicative evidence | Specific finding / gap | Next action
A-01 | Build, repository & local runtime | Inspect Build 13 branch and record immutable baseline commit | Yes | Partially implemented | No | Task-specific source cited | docs/BASELINE_PROVENANCE.json | Partially implemented: Inspect Build 13 branch and record immutable baseline commit. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
A-02 | Build, repository & local runtime | Create dependency inventory and supported-version matrix | Yes | Locally implemented | No | Task-specific source cited | docs/DEPENDENCY_AND_VERSION_MATRIX.md | Locally implemented: Create dependency inventory and supported-version matrix. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
A-03 | Build, repository & local runtime | Review licenses, CVEs and deprecated libraries | Yes | Partially implemented | No | Task-specific source cited | .github/dependabot.yml | Partially implemented: Review licenses, CVEs and deprecated libraries. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
A-04 | Build, repository & local runtime | Regenerate and commit reviewed npm lockfile | Yes | Prepared, not executed | No | Task-specific source cited | scripts/generate_reviewed_lockfile.sh | Lockfile generation script present, but reviewed lockfile not created. | Execute prepared procedure in a suitable local/staging environment and retain logs.
A-05 | Build, repository & local runtime | Compile backend with real Maven dependencies | Yes | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Maven runtime compilation not performed. | Execute prepared procedure in a suitable local/staging environment and retain logs.
A-06 | Build, repository & local runtime | Run backend unit and integration tests | Yes | Prepared, not executed | No | Task-specific source cited | apps/api/src/test | Prepared, not executed: Run backend unit and integration tests. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
A-07 | Build, repository & local runtime | Typecheck and production-build Next.js | Yes | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | TypeScript syntax checks do not replace npm typecheck/build. | Execute prepared procedure in a suitable local/staging environment and retain logs.
A-08 | Build, repository & local runtime | Build Docker images for API, frontend, worker and AI service | Yes | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Docker images have definitions; images have not been built here. | Execute prepared procedure in a suitable local/staging environment and retain logs.
A-09 | Build, repository & local runtime | Validate Compose schema, profiles and dependencies | Yes | Prepared, not executed | No | Task-specific source cited | compose.yaml | Prepared, not executed: Validate Compose schema, profiles and dependencies. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
A-10 | Build, repository & local runtime | Start PostgreSQL, Keycloak, Redis, RabbitMQ, MinIO, API, frontend and ML services | Yes | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Full Compose runtime has not been started. | Execute prepared procedure in a suitable local/staging environment and retain logs.
A-11 | Build, repository & local runtime | Apply Flyway V1–V9 on clean database and test an upgrade database | Yes | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | V1–V15 migrations exist; clean and upgrade PostgreSQL runs pending. | Execute prepared procedure in a suitable local/staging environment and retain logs.
A-12 | Build, repository & local runtime | Validate configuration/env contracts between containers | Yes | Locally implemented | No | Task-specific source cited | scripts/check_env_contracts.py | Locally implemented: Validate configuration/env contracts between containers. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
A-13 | Build, repository & local runtime | Fix first actual runtime errors with regression tests | Yes | Partially implemented | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Partially implemented: Fix first actual runtime errors with regression tests. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
A-14 | Build, repository & local runtime | Establish private Git repository, branches and protected PR workflow | No | Partially implemented | No | Task-specific source cited | .github/CODEOWNERS | Partially implemented: Establish private Git repository, branches and protected PR workflow. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
A-15 | Build, repository & local runtime | Centralize environment examples without committing secrets | No | Locally implemented | No | Task-specific source cited | .env.example | Locally implemented: Centralize environment examples without committing secrets. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
A-16 | Build, repository & local runtime | Produce reproducible clean-machine setup guide | No | Locally implemented | No | Task-specific source cited | docs/CLEAN_MACHINE_SETUP.md | Locally implemented: Produce reproducible clean-machine setup guide. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
B-01 | Identity, security & user accounts | Verify registration, login, email confirmation and account recovery | Yes | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Prepared, not executed: Verify registration, login, email confirmation and account recovery. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
B-02 | Identity, security & user accounts | Verify OIDC PKCE, issuer, audience, JWKS rotation and token refresh | Yes | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/security/TokenClaimsPolicy.java | JWT audience/client checks added; OIDC live rotation and token refresh pending. | Finish missing behavior, then verify in local integration and security tests.
B-03 | Identity, security & user accounts | Remove seeded/demo accounts from staging and production | Yes | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Prepared, not executed: Remove seeded/demo accounts from staging and production. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
B-04 | Identity, security & user accounts | Configure production identity persistence, SMTP and secure TLS | Yes | Externally blocked | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Externally blocked: Configure production identity persistence, SMTP and secure TLS. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
B-05 | Identity, security & user accounts | Enable MFA for administrators and sensitive accounts | Yes | Prepared, not executed | No | Task-specific source cited | scripts/generate_keycloak_staging_realm.py | Prepared, not executed: Enable MFA for administrators and sensitive accounts. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
B-06 | Identity, security & user accounts | Enforce viewer, creator, moderator and admin roles server-side | Yes | Partially implemented | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Partially implemented: Enforce viewer, creator, moderator and admin roles server-side. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
B-07 | Identity, security & user accounts | Enforce per-resource ownership and IDOR protection | Yes | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Prepared, not executed: Enforce per-resource ownership and IDOR protection. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
B-08 | Identity, security & user accounts | Add device/session inventory and revoke-all-sessions control | No | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/users/AccountSessionsController.java | ReelNest application sessions and API-token cutoff exist; IdP SSO revocation still pending. | Finish missing behavior, then verify in local integration and security tests.
B-09 | Identity, security & user accounts | Verify lockout, abuse throttling and stolen-token handling | No | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/security/AdmissionRateLimiter.java | Partially implemented: Verify lockout, abuse throttling and stolen-token handling. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
B-10 | Identity, security & user accounts | Add independent viewer profiles and PIN-protected adult profile actions | Yes | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Server-enforced profile PIN is not implemented. | Confirm no earlier implementation covers this requirement, then design/build and test.
B-11 | Identity, security & user accounts | Implement child ages, parental controls and mature-title restrictions | Yes | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/catalog/AgeRating.java | Partially implemented: Implement child ages, parental controls and mature-title restrictions. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
B-12 | Identity, security & user accounts | Add accessibility for authentication and account recovery | No | Partially implemented | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Partially implemented: Add accessibility for authentication and account recovery. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
B-13 | Identity, security & user accounts | Validate OIDC logout and cache/session invalidation | No | Partially implemented | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Partially implemented: Validate OIDC logout and cache/session invalidation. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
B-14 | Identity, security & user accounts | Test Keycloak outage, restart and identity recovery procedures | No | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Prepared, not executed: Test Keycloak outage, restart and identity recovery procedures. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
B-15 | Identity, security & user accounts | Review admin break-glass procedure and audit records | No | Prepared, not executed | No | Workstream-level source / documents only | docs/BUILD19_A_B_READINESS.md | Prepared, not executed: Review admin break-glass procedure and audit records. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
C-01 | Catalog, metadata, rights & moderation | Normalize movies, series, seasons, episodes and trailers | Yes | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/catalog/SeriesController.java | Partially implemented: Normalize movies, series, seasons, episodes and trailers. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
C-02 | Catalog, metadata, rights & moderation | Add creator-facing metadata validation and draft workflow | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/creators/CreatorTitleController.java | Locally implemented: Add creator-facing metadata validation and draft workflow. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
C-03 | Catalog, metadata, rights & moderation | Add genre, language, cast, crew, artwork and release metadata | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/catalog/TitleEntity.java | Partially implemented: Add genre, language, cast, crew, artwork and release metadata. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
C-04 | Catalog, metadata, rights & moderation | Add unique content identifiers, slugs and canonical URLs | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/catalog/TitleEntity.java | Partially implemented: Add unique content identifiers, slugs and canonical URLs. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
C-05 | Catalog, metadata, rights & moderation | Add posters, landscape art, banners and artwork rendition pipeline | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/catalog/TitleEntity.java | Partially implemented: Add posters, landscape art, banners and artwork rendition pipeline. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
C-06 | Catalog, metadata, rights & moderation | Add editorial categories, collections, featured rails and scheduling | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/catalog/TitleEntity.java | Partially implemented: Add editorial categories, collections, featured rails and scheduling. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
C-07 | Catalog, metadata, rights & moderation | Add search visibility rules and availability windows | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/catalog/PublicSeoController.java | Locally implemented: Add search visibility rules and availability windows. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
C-08 | Catalog, metadata, rights & moderation | Persist rights holder identity and attached licence evidence | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/catalog/TitleEntity.java | Partially implemented: Persist rights holder identity and attached licence evidence. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
C-09 | Catalog, metadata, rights & moderation | Model rights by country, region, platform, tier and date window | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/catalog/TitleEntity.java | Partially implemented: Model rights by country, region, platform, tier and date window. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
C-10 | Catalog, metadata, rights & moderation | Add content ratings, content warnings and age-review process | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/catalog/TitleEntity.java | Partially implemented: Add content ratings, content warnings and age-review process. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
C-11 | Catalog, metadata, rights & moderation | Implement reviewer approval/rejection and audit trails | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/rights/RightsController.java | Locally implemented: Implement reviewer approval/rejection and audit trails. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
C-12 | Catalog, metadata, rights & moderation | Enforce unpublish and rights revocation across search, CDN authorization and recommendations | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/catalog/TitleEntity.java | Partially implemented: Enforce unpublish and rights revocation across search, CDN authorization and recommendations. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
C-13 | Catalog, metadata, rights & moderation | Add takedown request and appeal workflows | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add takedown request and appeal workflows. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
C-14 | Catalog, metadata, rights & moderation | Implement metadata import/export and bulk operations | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Implement metadata import/export and bulk operations. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
C-15 | Catalog, metadata, rights & moderation | Review content rights and classification with qualified professionals | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/catalog/TitleEntity.java | Contracts, classifications and territory legal clearance require real reviewer. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
D-01 | Creator upload & media processing | Verify end-to-end direct multipart upload to private MinIO/S3 | Yes | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/uploads/UploadService.java | Upload code and integration scripts exist; real browser → MinIO → DB test pending. | Execute prepared procedure in a suitable local/staging environment and retain logs.
D-02 | Creator upload & media processing | Implement resumable interrupted uploads and safe retry | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/uploads/UploadService.java | Partially implemented: Implement resumable interrupted uploads and safe retry. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
D-03 | Creator upload & media processing | Enforce ownership, maximum size, format and quota constraints | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/uploads/UploadService.java | Partially implemented: Enforce ownership, maximum size, format and quota constraints. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
D-04 | Creator upload & media processing | Inspect input with ffprobe and reject malformed/disguised media | Yes | Locally implemented | No | Task-specific source cited | apps/video-worker/pipeline.py | Locally implemented: Inspect input with ffprobe and reject malformed/disguised media. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
D-05 | Creator upload & media processing | Isolate FFmpeg/worker execution and constrain resources | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/uploads/UploadService.java | Partially implemented: Isolate FFmpeg/worker execution and constrain resources. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
D-06 | Creator upload & media processing | Implement queue-claim leases and duplicate-job idempotency | Yes | Locally implemented | No | Task-specific source cited | apps/video-worker/worker.py | Locally implemented: Implement queue-claim leases and duplicate-job idempotency. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
D-07 | Creator upload & media processing | Generate aligned ABR renditions 360p/480p/720p/1080p | Yes | Locally implemented | No | Task-specific source cited | apps/video-worker/pipeline.py | FFmpeg HLS packaging tested offline; full encoding ladder must be verified per source/device. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
D-08 | Creator upload & media processing | Generate HLS master/media manifests with valid MIME and paths | Yes | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/uploads/UploadService.java | Locally implemented: Generate HLS master/media manifests with valid MIME and paths. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
D-09 | Creator upload & media processing | Generate optional DASH/CMAF renditions for multi-device playback | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Generate optional DASH/CMAF renditions for multi-device playback. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
D-10 | Creator upload & media processing | Create thumbnails, posters, preview strips and sprite/VTT metadata | Yes | Partially implemented | No | Task-specific source cited | apps/video-worker/preview_artwork.py | Partially implemented: Create thumbnails, posters, preview strips and sprite/VTT metadata. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
D-11 | Creator upload & media processing | Support alternate audio tracks and subtitle ingest | Yes | Partially implemented | No | Task-specific source cited | apps/video-worker/audio_packaging.py | Partially implemented: Support alternate audio tracks and subtitle ingest. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
D-12 | Creator upload & media processing | Add caption/transcript validation and timed-text conversion | Yes | Locally implemented | No | Task-specific source cited | apps/video-worker/timed_text.py | Locally implemented: Add caption/transcript validation and timed-text conversion. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
D-13 | Creator upload & media processing | Add 4K/HDR/HEVC/AV1 presets only for compatible devices/sources | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add 4K/HDR/HEVC/AV1 presets only for compatible devices/sources. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
D-14 | Creator upload & media processing | Record processing progress, ETA, warnings and failure diagnosis | No | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/uploads/MediaStatusController.java | Partially implemented: Record processing progress, ETA, warnings and failure diagnosis. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
D-15 | Creator upload & media processing | Implement retries, dead-letter queues, cancellation and cleanup | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/uploads/UploadService.java | Partially implemented: Implement retries, dead-letter queues, cancellation and cleanup. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
D-16 | Creator upload & media processing | Validate package decoding, manifest correctness and all segments | Yes | Partially implemented | No | Task-specific source cited | apps/video-worker/pipeline.py | Partially implemented: Validate package decoding, manifest correctness and all segments. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
D-17 | Creator upload & media processing | Prove publish gate requires encoded media and approved rights | Yes | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/uploads/UploadService.java | Locally implemented: Prove publish gate requires encoded media and approved rights. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
D-18 | Creator upload & media processing | Add lifecycle policies for originals, renditions and failed uploads | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/uploads/UploadService.java | Partially implemented: Add lifecycle policies for originals, renditions and failed uploads. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
E-01 | Netflix-style player & playback | Test initial playback in Chrome, Edge, Firefox and Safari | Yes | Prepared, not executed | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Prepared, not executed: Test initial playback in Chrome, Edge, Firefox and Safari. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
E-02 | Netflix-style player & playback | Test Android Chrome and iOS Safari native HLS behavior | Yes | Prepared, not executed | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Prepared, not executed: Test Android Chrome and iOS Safari native HLS behavior. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
E-03 | Netflix-style player & playback | Create responsive desktop, phone, tablet and TV player layouts | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Partially implemented: Create responsive desktop, phone, tablet and TV player layouts. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
E-04 | Netflix-style player & playback | Improve play, pause, seek, jump 10s, volume, mute and fullscreen | Yes | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Improve play, pause, seek, jump 10s, volume, mute and fullscreen. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-05 | Netflix-style player & playback | Implement adaptive quality auto-switching and manual quality selector | Yes | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Implement adaptive quality auto-switching and manual quality selector. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-06 | Netflix-style player & playback | Implement audio track and subtitle/closed-caption selectors | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Subtitle/alternate audio selectors exist; device and Safari end-to-end tracks unverified. | Finish missing behavior, then verify in local integration and security tests.
E-07 | Netflix-style player & playback | Implement subtitle styling: language, font size, contrast and positioning | Yes | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Implement subtitle styling: language, font size, contrast and positioning. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-08 | Netflix-style player & playback | Add persistent playback speed controls | No | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Add persistent playback speed controls. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-09 | Netflix-style player & playback | Implement accurate Continue Watching and multi-device resume | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/playback/ResumePolicy.java | Locally implemented: Implement accurate Continue Watching and multi-device resume. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-10 | Netflix-style player & playback | Add Next Episode, episode picker and series season navigation | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Episode navigation and Up Next source exists; full device focus/episode picker pending. | Finish missing behavior, then verify in local integration and security tests.
E-11 | Netflix-style player & playback | Add Skip Intro, Skip Recap and Skip Credits with metadata cues | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/playback/PlaybackCues.java | Locally implemented: Add Skip Intro, Skip Recap and Skip Credits with metadata cues. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-12 | Netflix-style player & playback | Implement Up Next countdown and disable-autoplay accessibility preference | Yes | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Implement Up Next countdown and disable-autoplay accessibility preference. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-13 | Netflix-style player & playback | Add spoiler-safe timeline previews and thumbnail scrubbing | Yes | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Add spoiler-safe timeline previews and thumbnail scrubbing. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-14 | Netflix-style player & playback | Add keyboard controls, focus rings and screen-reader descriptions | No | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Add keyboard controls, focus rings and screen-reader descriptions. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-15 | Netflix-style player & playback | Add touch gestures and orientation/rotation handling | No | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Add touch gestures and orientation/rotation handling. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-16 | Netflix-style player & playback | Implement picture-in-picture where supported | No | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Implement picture-in-picture where supported. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-17 | Netflix-style player & playback | Add Chromecast/AirPlay casting when platforms permit | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add Chromecast/AirPlay casting when platforms permit. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
E-18 | Netflix-style player & playback | Gracefully recover network loss, buffering and expired authorization | Yes | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Gracefully recover network loss, buffering and expired authorization. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-19 | Netflix-style player & playback | Provide playback error codes, retry action and user-facing diagnostics | Yes | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Provide playback error codes, retry action and user-facing diagnostics. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-20 | Netflix-style player & playback | Tune startup latency, buffer size, ABR ladder and rebuffering controls | No | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Partially implemented: Tune startup latency, buffer size, ABR ladder and rebuffering controls. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
E-21 | Netflix-style player & playback | Support data-saver and optional audio-only accessibility mode | No | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Partially implemented: Support data-saver and optional audio-only accessibility mode. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
E-22 | Netflix-style player & playback | Handle subtitle/audio language preference per profile | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/playback/PlayerPreferencesController.java | Locally implemented: Handle subtitle/audio language preference per profile. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-23 | Netflix-style player & playback | Capture playback QoE events with consent and privacy limits | No | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Locally implemented: Capture playback QoE events with consent and privacy limits. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
E-24 | Netflix-style player & playback | Verify stream session limits across browsers/devices | No | Prepared, not executed | No | Workstream-level source / documents only | apps/web/src/app/watch/[id]/page.tsx | Prepared, not executed: Verify stream session limits across browsers/devices. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
F-01 | DRM, entitlement & streaming security | Verify every playback API checks profile ownership | Yes | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Prepared, not executed: Verify every playback API checks profile ownership. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
F-02 | DRM, entitlement & streaming security | Verify subscription, free tier, rentals and trials when configured | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Partially implemented: Verify subscription, free tier, rentals and trials when configured. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
F-03 | DRM, entitlement & streaming security | Verify publication, age, territory and rights dates on every session | Yes | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Locally implemented: Verify publication, age, territory and rights dates on every session. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
F-04 | DRM, entitlement & streaming security | Implement trusted country decision from edge/network signal, not client input | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Territory restrictions are partially modeled; trusted edge country enforcement not verified. | Finish missing behavior, then verify in local integration and security tests.
F-05 | DRM, entitlement & streaming security | Generate short-lived scoped CloudFront signed cookies/URLs | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/playback/CdnCookieSigner.java | Locally implemented: Generate short-lived scoped CloudFront signed cookies/URLs. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
F-06 | DRM, entitlement & streaming security | Prove direct S3 and unauthorized CDN requests return denial | Yes | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Prepared, not executed: Prove direct S3 and unauthorized CDN requests return denial. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
F-07 | DRM, entitlement & streaming security | Verify session renewal and revoked subscription/rights handling | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Partially implemented: Verify session renewal and revoked subscription/rights handling. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
F-08 | DRM, entitlement & streaming security | Implement CDN edge/token key rotation and private key custody | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Partially implemented: Implement CDN edge/token key rotation and private key custody. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
F-09 | DRM, entitlement & streaming security | Prevent manifest and segment authorization bypass | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Locally implemented: Prevent manifest and segment authorization bypass. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
F-10 | DRM, entitlement & streaming security | Support concurrent stream leases and shared account device policy | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Partially implemented: Support concurrent stream leases and shared account device policy. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
F-11 | DRM, entitlement & streaming security | Add optional session anomaly detection and suspicious activity reviews | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add optional session anomaly detection and suspicious activity reviews. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
F-12 | DRM, entitlement & streaming security | Design DRM packaging and SPEKE/license-server integration | Yes | Not started / no evidence found | No | Workstream-level source / documents only | None identified | No verified commercial DRM vendor/server integration. | Confirm no earlier implementation covers this requirement, then design/build and test.
F-13 | DRM, entitlement & streaming security | Integrate Widevine on supported browser/Android clients | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Integrate Widevine on supported browser/Android clients. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
F-14 | DRM, entitlement & streaming security | Integrate FairPlay for Safari/iOS/tvOS clients | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Integrate FairPlay for Safari/iOS/tvOS clients. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
F-15 | DRM, entitlement & streaming security | Integrate PlayReady for Windows/selected TV clients | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Integrate PlayReady for Windows/selected TV clients. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
F-16 | DRM, entitlement & streaming security | Add device capabilities/fallbacks and verify license renewals | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add device capabilities/fallbacks and verify license renewals. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
F-17 | DRM, entitlement & streaming security | Implement rights-driven watermarking or forensic watermark vendor integration | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Implement rights-driven watermarking or forensic watermark vendor integration. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
F-18 | DRM, entitlement & streaming security | Test offline DRM licences where offline downloads are permitted | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Test offline DRM licences where offline downloads are permitted. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
F-19 | DRM, entitlement & streaming security | Define DRM compliance and security commitments with licensors | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PrivateMediaController.java | Externally blocked: Define DRM compliance and security commitments with licensors. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
G-01 | Subscriptions & international payments | Compile and run billing service against local database | Yes | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/billing/BillingService.java | Prepared, not executed: Compile and run billing service against local database. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
G-02 | Subscriptions & international payments | Verify Razorpay TEST plan creation and checkout | Yes | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/billing/BillingService.java | Razorpay test keys and actual sandbox callbacks needed. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
G-03 | Subscriptions & international payments | Validate raw-body webhook signatures and event IDs | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/billing/WebhookVerifier.java | Raw-body webhook verification code is present; live provider webhook test pending. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
G-04 | Subscriptions & international payments | Handle captured, failed, pending, duplicate and out-of-order events | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/billing/BillingService.java | Partially implemented: Handle captured, failed, pending, duplicate and out-of-order events. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
G-05 | Subscriptions & international payments | Use verified charges and paid-through dates for premium entitlement | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/billing/EntitlementPolicy.java | Locally implemented: Use verified charges and paid-through dates for premium entitlement. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
G-06 | Subscriptions & international payments | Verify trial, renewal, grace period and expired subscriptions | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/billing/BillingService.java | Partially implemented: Verify trial, renewal, grace period and expired subscriptions. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
G-07 | Subscriptions & international payments | Verify cancellation now versus period-end behavior | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/billing/BillingService.java | Partially implemented: Verify cancellation now versus period-end behavior. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
G-08 | Subscriptions & international payments | Handle full and partial refunds and dispute/chargeback reversals | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/billing/ChargePolicy.java | Locally implemented: Handle full and partial refunds and dispute/chargeback reversals. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
G-09 | Subscriptions & international payments | Reconcile provider events against database and report discrepancies | Yes | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/billing/BillingReconciliationJob.java | Partially implemented: Reconcile provider events against database and report discrepancies. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
G-10 | Subscriptions & international payments | Add upgrade, downgrade, prorating and plan-change UX | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add upgrade, downgrade, prorating and plan-change UX. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
G-11 | Subscriptions & international payments | Define trials, coupons, promotional credits and abuse prevention | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Define trials, coupons, promotional credits and abuse prevention. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
G-12 | Subscriptions & international payments | Add invoices, tax information and payment failure communication | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/billing/BillingService.java | Partially implemented: Add invoices, tax information and payment failure communication. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
G-13 | Subscriptions & international payments | Support subscriptions per country/currency only where provider allows | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Support subscriptions per country/currency only where provider allows. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
G-14 | Subscriptions & international payments | Implement international payment method/provider abstraction | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Implement international payment method/provider abstraction. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
G-15 | Subscriptions & international payments | Calculate appropriate local taxes, VAT/GST and refund rules with advisor | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/billing/BillingService.java | Externally blocked: Calculate appropriate local taxes, VAT/GST and refund rules with advisor. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
G-16 | Subscriptions & international payments | Define paid film rentals/TVOD and purchase windows (optional) | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Define paid film rentals/TVOD and purchase windows (optional). Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
G-17 | Subscriptions & international payments | Verify PCI/payment scope; never store sensitive card credentials | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/billing/BillingService.java | Partially implemented: Verify PCI/payment scope; never store sensitive card credentials. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
H-01 | Search, recommendations & AI | Verify baseline keyword search, facets and synonyms | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/discovery/PrivateRecommendationClient.java | Partially implemented: Verify baseline keyword search, facets and synonyms. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
H-02 | Search, recommendations & AI | Improve multilingual and transliterated title discovery | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Improve multilingual and transliterated title discovery. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
H-03 | Search, recommendations & AI | Verify cold-start onboarding and trending recommendations | Yes | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/discovery/PrivateRecommendationClient.java | Locally implemented: Verify cold-start onboarding and trending recommendations. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
H-04 | Search, recommendations & AI | Validate personalized ranking only on eligible titles | Yes | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/discovery/PrivateRecommendationClient.java | Locally implemented: Validate personalized ranking only on eligible titles. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
H-05 | Search, recommendations & AI | Connect private recommendation service to live API with feature flag | Yes | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/discovery/PrivateRecommendationClient.java | ML API client is present; live integration/feature flag behavior unverified. | Finish missing behavior, then verify in local integration and security tests.
H-06 | Search, recommendations & AI | Ensure unauthorized content never appears from ML fallback | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/discovery/PrivateRecommendationClient.java | Partially implemented: Ensure unauthorized content never appears from ML fallback. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
H-07 | Search, recommendations & AI | Create offline chronological evaluation and reproducible datasets | Yes | Locally implemented | No | Task-specific source cited | apps/recommendation-lab/evaluation.py | Offline chronological model evaluation exists; no online performance certification. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
H-08 | Search, recommendations & AI | Measure Recall@K, NDCG@K, coverage, diversity and fairness | Yes | Locally implemented | No | Task-specific source cited | apps/recommendation-lab/evaluation.py | Locally implemented: Measure Recall@K, NDCG@K, coverage, diversity and fairness. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
H-09 | Search, recommendations & AI | Add semantic search with title/synopsis embeddings | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add semantic search with title/synopsis embeddings. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
H-10 | Search, recommendations & AI | Add collaborative filtering candidate generator after sufficient data | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/discovery/PrivateRecommendationClient.java | Partially implemented: Add collaborative filtering candidate generator after sufficient data. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
H-11 | Search, recommendations & AI | Add hybrid retrieval, reranking and exploration strategies | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/discovery/PrivateRecommendationClient.java | Partially implemented: Add hybrid retrieval, reranking and exploration strategies. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
H-12 | Search, recommendations & AI | Add per-user control for personalization and privacy | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/discovery/PrivateRecommendationClient.java | Partially implemented: Add per-user control for personalization and privacy. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
H-13 | Search, recommendations & AI | Train/update models with versioned features and drift monitoring | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Train/update models with versioned features and drift monitoring. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
H-14 | Search, recommendations & AI | Set up online experiments, holdouts and unbiased metrics | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Set up online experiments, holdouts and unbiased metrics. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
H-15 | Search, recommendations & AI | Build editorial overrides, safety exclusion and diversity constraints | No | Locally implemented | No | Task-specific source cited | apps/recommendation-lab/evaluation.py | Locally implemented: Build editorial overrides, safety exclusion and diversity constraints. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
H-16 | Search, recommendations & AI | Optional AI scene search and natural-language content discovery | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Optional AI scene search and natural-language content discovery. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
H-17 | Search, recommendations & AI | Optional assisted subtitles/transcripts/dubbing with human QA | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/discovery/PrivateRecommendationClient.java | Partially implemented: Optional assisted subtitles/transcripts/dubbing with human QA. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
I-01 | Analytics & quality of experience | Validate view events and event retention controls | Yes | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PlaybackQoeController.java | Locally implemented: Validate view events and event retention controls. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
I-02 | Analytics & quality of experience | Instrument request tracing and correlation IDs | No | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PlaybackQoeController.java | Locally implemented: Instrument request tracing and correlation IDs. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
I-03 | Analytics & quality of experience | Capture startup time, bitrate switches, stalls and player errors | Yes | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/playback/PlaybackQoeController.java | Locally implemented: Capture startup time, bitrate switches, stalls and player errors. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
I-04 | Analytics & quality of experience | Implement active-users, conversions, retention, churn and watch time | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PlaybackQoeController.java | Partially implemented: Implement active-users, conversions, retention, churn and watch time. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
I-05 | Analytics & quality of experience | Add movie/episode completion and drop-off funnels | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PlaybackQoeController.java | Partially implemented: Add movie/episode completion and drop-off funnels. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
I-06 | Analytics & quality of experience | Build content viewing heatmaps and episodic analytics | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Build content viewing heatmaps and episodic analytics. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
I-07 | Analytics & quality of experience | Build creator dashboard for views, audience and revenue share | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PlaybackQoeController.java | Partially implemented: Build creator dashboard for views, audience and revenue share. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
I-08 | Analytics & quality of experience | Design privacy-safe event schema and identity resolution | Yes | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PlaybackQoeController.java | Locally implemented: Design privacy-safe event schema and identity resolution. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
I-09 | Analytics & quality of experience | Add event deduplication, ingestion durability and replay | Yes | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/playback/PlaybackQoeController.java | Partially implemented: Add event deduplication, ingestion durability and replay. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
I-10 | Analytics & quality of experience | Implement exportable admin dashboards with RBAC | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/playback/PlaybackQoeController.java | Partially implemented: Implement exportable admin dashboards with RBAC. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
I-11 | Analytics & quality of experience | Add cohort analysis and acquisition attribution with consent | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add cohort analysis and acquisition attribution with consent. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
I-12 | Analytics & quality of experience | Set up data quality alerts, anomalies and schema-version handling | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Set up data quality alerts, anomalies and schema-version handling. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
I-13 | Analytics & quality of experience | Benchmark streaming QoE by country/ISP/device | Yes | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Benchmark streaming QoE by country/ISP/device. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
J-01 | UI, accessibility & localization | Verify every existing route and error state in the real app | Yes | Prepared, not executed | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Prepared, not executed: Verify every existing route and error state in the real app. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
J-02 | UI, accessibility & localization | Unify original ReelNest brand identity and design tokens | No | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Partially implemented: Unify original ReelNest brand identity and design tokens. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
J-03 | UI, accessibility & localization | Build hero banners, collections, titles and episode detail UX | No | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Locally implemented: Build hero banners, collections, titles and episode detail UX. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
J-04 | UI, accessibility & localization | Add responsive navigation, profile picker, watchlist and search | Yes | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Locally implemented: Add responsive navigation, profile picker, watchlist and search. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
J-05 | UI, accessibility & localization | Add loading skeletons, empty states and safe fallbacks | Yes | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Locally implemented: Add loading skeletons, empty states and safe fallbacks. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
J-06 | UI, accessibility & localization | Provide screen-reader labels, keyboard nav and WCAG audits | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Partially implemented: Provide screen-reader labels, keyboard nav and WCAG audits. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
J-07 | UI, accessibility & localization | Provide Hindi/English localizations with translation architecture | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Partially implemented: Provide Hindi/English localizations with translation architecture. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
J-08 | UI, accessibility & localization | Design RTL layout support for applicable languages | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Design RTL layout support for applicable languages. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
J-09 | UI, accessibility & localization | Add profile-specific recommendations and personalized home rails | No | Locally implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Locally implemented: Add profile-specific recommendations and personalized home rails. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
J-10 | UI, accessibility & localization | Add themed posters, trailers, preview thumbnails and editorial art | No | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Partially implemented: Add themed posters, trailers, preview thumbnails and editorial art. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
J-11 | UI, accessibility & localization | Implement support/contact, FAQ and account settings pages | No | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Partially implemented: Implement support/contact, FAQ and account settings pages. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
J-12 | UI, accessibility & localization | Add notifications, parental settings and device management UX | No | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/browse/page.tsx | Partially implemented: Add notifications, parental settings and device management UX. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
J-13 | UI, accessibility & localization | Implement SEO, social previews, sitemap and metadata for public content | Yes | Locally implemented | No | Task-specific source cited | apps/web/src/app/sitemap.ts | Locally implemented: Implement SEO, social previews, sitemap and metadata for public content. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
J-14 | UI, accessibility & localization | Add opt-in email/push notifications respecting consent | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add opt-in email/push notifications respecting consent. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
K-01 | Creator Studio & administration | Creator verification and contract upload review | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/creator/page.tsx | Partially implemented: Creator verification and contract upload review. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
K-02 | Creator Studio & administration | Creator content submission, resubmission and versioning | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/creator/page.tsx | Partially implemented: Creator content submission, resubmission and versioning. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
K-03 | Creator Studio & administration | Admin role separation, two-person approval for sensitive actions | No | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/creator/page.tsx | Partially implemented: Admin role separation, two-person approval for sensitive actions. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
K-04 | Creator Studio & administration | Bulk catalog updates and metadata import/export | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Bulk catalog updates and metadata import/export. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
K-05 | Creator Studio & administration | Rights calendar, expiration alerts and takedown controls | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/creator/page.tsx | Partially implemented: Rights calendar, expiration alerts and takedown controls. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
K-06 | Creator Studio & administration | Admin complaints, moderation decisions and appeal case management | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Admin complaints, moderation decisions and appeal case management. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
K-07 | Creator Studio & administration | Creator processing dashboard, subtitles and poster editing | Yes | Partially implemented | No | Task-specific source cited | apps/web/src/app/creator/page.tsx | Partially implemented: Creator processing dashboard, subtitles and poster editing. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
K-08 | Creator Studio & administration | Creator earnings statements and configurable revenue share | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Creator earnings statements and configurable revenue share. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
K-09 | Creator Studio & administration | Support tickets, transaction investigations and viewer complaints | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Support tickets, transaction investigations and viewer complaints. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
K-10 | Creator Studio & administration | Refund-support tools with auditable approval workflow | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Refund-support tools with auditable approval workflow. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
K-11 | Creator Studio & administration | Operations dashboard for worker failures and playback errors | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/src/app/creator/page.tsx | Partially implemented: Operations dashboard for worker failures and playback errors. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
K-12 | Creator Studio & administration | Content publishing schedules, embargoes and staged rollouts | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Content publishing schedules, embargoes and staged rollouts. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
K-13 | Creator Studio & administration | Rights-holder reports and platform audit exports | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Rights-holder reports and platform audit exports. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
L-01 | AWS & worldwide distribution | Verify local Docker integration before AWS deployment | Yes | Prepared, not executed | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Prepared, not executed: Verify local Docker integration before AWS deployment. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
L-02 | AWS & worldwide distribution | Validate Terraform fmt/init/validate with real providers | Yes | Prepared, not executed | No | Task-specific source cited | infrastructure/aws/versions.tf | Prepared, not executed: Validate Terraform fmt/init/validate with real providers. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
L-03 | AWS & worldwide distribution | Review Terraform plan, resource costs and IAM policies | Yes | Prepared, not executed | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Prepared, not executed: Review Terraform plan, resource costs and IAM policies. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
L-04 | AWS & worldwide distribution | Configure separate dev/staging/prod AWS accounts or roles | No | Partially implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Partially implemented: Configure separate dev/staging/prod AWS accounts or roles. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
L-05 | AWS & worldwide distribution | Configure private VPC, subnets, NAT, security groups and endpoints | No | Locally implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Locally implemented: Configure private VPC, subnets, NAT, security groups and endpoints. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
L-06 | AWS & worldwide distribution | Provision RDS PostgreSQL with backup and runtime least privilege | Yes | Locally implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Locally implemented: Provision RDS PostgreSQL with backup and runtime least privilege. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
L-07 | AWS & worldwide distribution | Provision Redis, message broker, ECS services and job workers | Yes | Locally implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Locally implemented: Provision Redis, message broker, ECS services and job workers. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
L-08 | AWS & worldwide distribution | Configure IAM roles, Secrets Manager and key rotation | Yes | Partially implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Partially implemented: Configure IAM roles, Secrets Manager and key rotation. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
L-09 | AWS & worldwide distribution | Publish reproducible ECR container images and digest pins | No | Partially implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Partially implemented: Publish reproducible ECR container images and digest pins. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
L-10 | AWS & worldwide distribution | Configure managed Keycloak or supported OIDC runtime | Yes | Partially implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Partially implemented: Configure managed Keycloak or supported OIDC runtime. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
L-11 | AWS & worldwide distribution | Deploy frontend, API, ML service and worker to staging | Yes | Prepared, not executed | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Prepared, not executed: Deploy frontend, API, ML service and worker to staging. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
L-12 | AWS & worldwide distribution | Configure Route 53 DNS, TLS/ACM and custom app/API/stream hostnames | Yes | Partially implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Partially implemented: Configure Route 53 DNS, TLS/ACM and custom app/API/stream hostnames. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
L-13 | AWS & worldwide distribution | Configure private S3 storage and CloudFront OAC origins | Yes | Locally implemented | No | Task-specific source cited | infrastructure/aws/media.tf | Locally implemented: Configure private S3 storage and CloudFront OAC origins. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
L-14 | AWS & worldwide distribution | Configure signed-cookies distribution and verified georestrictions | Yes | Prepared, not executed | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/playback/CdnCookieSigner.java | Prepared, not executed: Configure signed-cookies distribution and verified georestrictions. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
L-15 | AWS & worldwide distribution | Deploy CloudFront global distribution and verify real regional clients | Yes | Externally blocked | No | Workstream-level source / documents only | infrastructure/aws/services.tf | CloudFront Terraform is not proof of multi-country service operation. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
L-16 | AWS & worldwide distribution | Implement country-specific catalog, tier and entitlement policies | No | Partially implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Partially implemented: Implement country-specific catalog, tier and entitlement policies. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
L-17 | AWS & worldwide distribution | Measure CDN cache hit rate, bandwidth, misses and origin egress | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Measure CDN cache hit rate, bandwidth, misses and origin egress. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
L-18 | AWS & worldwide distribution | Set cost budgets, quotas, alerts and encoder spend safeguards | No | Partially implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Partially implemented: Set cost budgets, quotas, alerts and encoder spend safeguards. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
L-19 | AWS & worldwide distribution | Configure origin shield/multi-region origins only after measured need | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Configure origin shield/multi-region origins only after measured need. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
L-20 | AWS & worldwide distribution | Design global API latency and disaster recovery strategy | No | Prepared, not executed | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Prepared, not executed: Design global API latency and disaster recovery strategy. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
L-21 | AWS & worldwide distribution | Add regional API deployment, Route53 latency routing when justified | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add regional API deployment, Route53 latency routing when justified. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
L-22 | AWS & worldwide distribution | Plan database cross-region replication and consistency/failover | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Plan database cross-region replication and consistency/failover. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
L-23 | AWS & worldwide distribution | Implement progressive delivery, rollback and environment promotion | No | Partially implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Partially implemented: Implement progressive delivery, rollback and environment promotion. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
L-24 | AWS & worldwide distribution | Set up streaming DNS, cache invalidation and emergency block controls | No | Partially implemented | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Partially implemented: Set up streaming DNS, cache invalidation and emergency block controls. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
L-25 | AWS & worldwide distribution | Perform canary pilot in one licensed territory before worldwide rollout | No | Externally blocked | No | Workstream-level source / documents only | infrastructure/aws/services.tf | Externally blocked: Perform canary pilot in one licensed territory before worldwide rollout. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
M-01 | Mobile, TV & offline viewing | Harden installable PWA manifest, service worker and app shell | Yes | Partially implemented | No | Workstream-level source / documents only | apps/web/public/manifest.webmanifest | PWA manifest exists, offline app-shell/service worker completeness unverified. | Finish missing behavior, then verify in local integration and security tests.
M-02 | Mobile, TV & offline viewing | Create Android app with compatible playback/DRM framework | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Create Android app with compatible playback/DRM framework. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-03 | Mobile, TV & offline viewing | Create iOS app with AVPlayer/FairPlay compatibility | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Create iOS app with AVPlayer/FairPlay compatibility. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-04 | Mobile, TV & offline viewing | Test Android/iOS auth flows and deep links | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Test Android/iOS auth flows and deep links. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-05 | Mobile, TV & offline viewing | Implement mobile download manager only for authorized offline titles | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Implement mobile download manager only for authorized offline titles. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-06 | Mobile, TV & offline viewing | Handle expiration, key renewal and delete downloaded media | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Handle expiration, key renewal and delete downloaded media. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-07 | Mobile, TV & offline viewing | Build Android TV / Google TV focus-based player UX | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Build Android TV / Google TV focus-based player UX. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-08 | Mobile, TV & offline viewing | Build Apple tvOS player and focus/navigation UX | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Build Apple tvOS player and focus/navigation UX. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-09 | Mobile, TV & offline viewing | Add Samsung Tizen client where market warrants | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add Samsung Tizen client where market warrants. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-10 | Mobile, TV & offline viewing | Add LG webOS client where market warrants | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add LG webOS client where market warrants. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-11 | Mobile, TV & offline viewing | Implement remote control focus map, D-pad and accessibility | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Implement remote control focus map, D-pad and accessibility. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-12 | Mobile, TV & offline viewing | Implement casting/deep-link handoff and device pairing | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Implement casting/deep-link handoff and device pairing. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-13 | Mobile, TV & offline viewing | Set up push notifications, privacy prompts and crash analytics | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Set up push notifications, privacy prompts and crash analytics. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
M-14 | Mobile, TV & offline viewing | Set up app signing, store listings, review and staged rollouts | No | Externally blocked | No | Workstream-level source / documents only | apps/web/public/manifest.webmanifest | Externally blocked: Set up app signing, store listings, review and staged rollouts. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
M-15 | Mobile, TV & offline viewing | Create a device/browser/DRM capability matrix and test lab | No | Prepared, not executed | No | Workstream-level source / documents only | apps/web/public/manifest.webmanifest | Prepared, not executed: Create a device/browser/DRM capability matrix and test lab. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
N-01 | Privacy, legal & compliance | Review privacy policy, terms of use and applicable data laws | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Externally blocked: Review privacy policy, terms of use and applicable data laws. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
N-02 | Privacy, legal & compliance | Complete account export and deletion across identity and database | Yes | Partially implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Limited free-viewer erasure path exists; legal retention and live propagation pending. | Finish missing behavior, then verify in local integration and security tests.
N-03 | Privacy, legal & compliance | Respect billing/creator/audit record retention exemptions | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Partially implemented: Respect billing/creator/audit record retention exemptions. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
N-04 | Privacy, legal & compliance | Implement deletion propagation to analytics, caches and object storage | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Partially implemented: Implement deletion propagation to analytics, caches and object storage. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
N-05 | Privacy, legal & compliance | Define data retention schedule and backup deletion/expiry procedure | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Partially implemented: Define data retention schedule and backup deletion/expiry procedure. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
N-06 | Privacy, legal & compliance | Add consent, cookie tracking preferences and policy versioning | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Partially implemented: Add consent, cookie tracking preferences and policy versioning. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
N-07 | Privacy, legal & compliance | Perform child data/age verification risk review | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Externally blocked: Perform child data/age verification risk review. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
N-08 | Privacy, legal & compliance | Review OTT content classifications, grievance redressal and takedown | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Externally blocked: Review OTT content classifications, grievance redressal and takedown. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
N-09 | Privacy, legal & compliance | Validate rights contracts for every country and streaming platform | Yes | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Externally blocked: Validate rights contracts for every country and streaming platform. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
N-10 | Privacy, legal & compliance | Review international taxes, trade/sanctions and payment availability | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Externally blocked: Review international taxes, trade/sanctions and payment availability. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
N-11 | Privacy, legal & compliance | Review accessibility commitments in target countries | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Externally blocked: Review accessibility commitments in target countries. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
N-12 | Privacy, legal & compliance | Maintain security incident, legal hold and deletion audit logs | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Partially implemented: Maintain security incident, legal hold and deletion audit logs. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
N-13 | Privacy, legal & compliance | Run independent IP/trademark clearance for brand name and artwork | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Externally blocked: Run independent IP/trademark clearance for brand name and artwork. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
N-14 | Privacy, legal & compliance | Define creator payout and intellectual-property dispute process | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Externally blocked: Define creator payout and intellectual-property dispute process. Obtain the required account, provider service, deployment authorization or professional approval; then verify. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
N-15 | Privacy, legal & compliance | Document media licensing, DRM and geoblocking limitations | No | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/privacy/PrivacyErasureService.java | Prepared, not executed: Document media licensing, DRM and geoblocking limitations. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
O-01 | Security & engineering quality | Create system threat model, assets inventory and trust boundaries | No | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Prepared, not executed: Create system threat model, assets inventory and trust boundaries. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
O-02 | Security & engineering quality | Enforce authentication on all private API/media routes | Yes | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Partially implemented: Enforce authentication on all private API/media routes. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
O-03 | Security & engineering quality | Test BOLA/IDOR against user/creator/admin account boundaries | Yes | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Prepared, not executed: Test BOLA/IDOR against user/creator/admin account boundaries. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
O-04 | Security & engineering quality | Test CSRF/CORS/cookie scope and browser sandboxing | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Partially implemented: Test CSRF/CORS/cookie scope and browser sandboxing. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
O-05 | Security & engineering quality | Perform input validation, injection and XSS regression tests | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Partially implemented: Perform input validation, injection and XSS regression tests. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
O-06 | Security & engineering quality | Secure multipart upload, MIME sniffing and archive/path traversal | No | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Locally implemented: Secure multipart upload, MIME sniffing and archive/path traversal. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
O-07 | Security & engineering quality | Add SAST/SCA/dependency and secret scanning to CI | No | Partially implemented | No | Task-specific source cited | .github/workflows/checks.yml | Partially implemented: Add SAST/SCA/dependency and secret scanning to CI. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
O-08 | Security & engineering quality | Apply restrictive CSP, HSTS, secure headers and TLS settings | No | Locally implemented | No | Task-specific source cited | apps/api/src/main/java/com/reelnest/security/RequestSecurityHeaders.java | Locally implemented: Apply restrictive CSP, HSTS, secure headers and TLS settings. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
O-09 | Security & engineering quality | Run DAST and external dependency/vulnerability review | No | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Prepared, not executed: Run DAST and external dependency/vulnerability review. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
O-10 | Security & engineering quality | Review least-privilege IAM, SQL runtime privileges and admin MFA | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Partially implemented: Review least-privilege IAM, SQL runtime privileges and admin MFA. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
O-11 | Security & engineering quality | Implement webhook rate limiting, request signing and replay defense | No | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Locally implemented: Implement webhook rate limiting, request signing and replay defense. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
O-12 | Security & engineering quality | Test CDN signed-cookie expiry, geo bypass and authorization revocation | No | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Prepared, not executed: Test CDN signed-cookie expiry, geo bypass and authorization revocation. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
O-13 | Security & engineering quality | Add pentest and independent security review before paid launch | No | Externally blocked | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Independent security assessment not performed. | Obtain the required account, provider service, deployment authorization or professional approval; then verify.
O-14 | Security & engineering quality | Implement deterministic fixtures and contract/unit/integration tests | No | Locally implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Locally implemented: Implement deterministic fixtures and contract/unit/integration tests. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
O-15 | Security & engineering quality | Add Playwright happy-path and negative browser E2E flows | No | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Prepared, not executed: Add Playwright happy-path and negative browser E2E flows. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
O-16 | Security & engineering quality | Add visual, keyboard, browser matrix and accessibility regressions | No | Prepared, not executed | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Prepared, not executed: Add visual, keyboard, browser matrix and accessibility regressions. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
O-17 | Security & engineering quality | Establish performance budgets for API, player and web app | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Partially implemented: Establish performance budgets for API, player and web app. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
O-18 | Security & engineering quality | Add regression tests for each fixed P0/P1 bug | No | Partially implemented | No | Workstream-level source / documents only | apps/api/src/main/java/com/reelnest/security/SecurityConfig.java | Partially implemented: Add regression tests for each fixed P0/P1 bug. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
P-01 | Reliability, performance & recovery | Run backup/restore in disposable PostgreSQL environment | Yes | Prepared, not executed | No | Task-specific source cited | scripts/test_restore_disposable.sh | Disposable backup/restore test script exists but has not been executed. | Execute prepared procedure in a suitable local/staging environment and retain logs.
P-02 | Reliability, performance & recovery | Measure backup recovery-point and recovery-time objectives | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Measure backup recovery-point and recovery-time objectives. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
P-03 | Reliability, performance & recovery | Verify durable worker retry/dead-letter/crash recovery | No | Partially implemented | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Partially implemented: Verify durable worker retry/dead-letter/crash recovery. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
P-04 | Reliability, performance & recovery | Run read-only and controlled-write load tests in staging | No | Prepared, not executed | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Prepared, not executed: Run read-only and controlled-write load tests in staging. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
P-05 | Reliability, performance & recovery | Test playback startup time and rebuffer ratios across networks | No | Prepared, not executed | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Prepared, not executed: Test playback startup time and rebuffer ratios across networks. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
P-06 | Reliability, performance & recovery | Load test simultaneous sessions and subscription gate | No | Prepared, not executed | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Prepared, not executed: Load test simultaneous sessions and subscription gate. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
P-07 | Reliability, performance & recovery | Verify monitoring dashboards, on-call alerts and logging | No | Partially implemented | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Partially implemented: Verify monitoring dashboards, on-call alerts and logging. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
P-08 | Reliability, performance & recovery | Test disk/storage, DB, broker and upstream outage behavior | No | Prepared, not executed | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Prepared, not executed: Test disk/storage, DB, broker and upstream outage behavior. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
P-09 | Reliability, performance & recovery | Implement readiness/liveness probes and graceful shutdown | No | Partially implemented | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Partially implemented: Implement readiness/liveness probes and graceful shutdown. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
P-10 | Reliability, performance & recovery | Use auto-scaling only after testing predictable thresholds | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Use auto-scaling only after testing predictable thresholds. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
P-11 | Reliability, performance & recovery | Test blue-green/canary deploy and safe rollback | No | Prepared, not executed | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Prepared, not executed: Test blue-green/canary deploy and safe rollback. Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
P-12 | Reliability, performance & recovery | Configure retention and cost alarms for logs, storage and CDN | No | Partially implemented | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Partially implemented: Configure retention and cost alarms for logs, storage and CDN. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
P-13 | Reliability, performance & recovery | Document incident response, rollback and on-call runbooks | No | Locally implemented | No | Task-specific source cited | docs/OPERATIONS_RUNBOOK.md | Locally implemented: Document incident response, rollback and on-call runbooks. Run task-specific acceptance tests against the real app; inspect remaining edge cases. | Run task-specific acceptance tests against the real app; inspect remaining edge cases.
P-14 | Reliability, performance & recovery | Perform chaos/failure injection in staging (not production) | No | Prepared, not executed | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Prepared, not executed: Perform chaos/failure injection in staging (not production). Execute prepared procedure in a suitable local/staging environment and retain logs. | Execute prepared procedure in a suitable local/staging environment and retain logs.
P-15 | Reliability, performance & recovery | Create reproducible launch audit/evidence package | No | Partially implemented | No | Workstream-level source / documents only | scripts/test_restore_disposable.sh | Partially implemented: Create reproducible launch audit/evidence package. Finish missing behavior, then verify in local integration and security tests. | Finish missing behavior, then verify in local integration and security tests.
Q-01 | Advanced innovation & monetization | Introduce AVOD advertising with server/client insertion where permitted | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Introduce AVOD advertising with server/client insertion where permitted. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-02 | Advanced innovation & monetization | Offer AVOD/SVOD/TVOD hybrid packages and experiments | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Offer AVOD/SVOD/TVOD hybrid packages and experiments. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-03 | Advanced innovation & monetization | Implement live events with separate ingest and low-latency pipeline | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Implement live events with separate ingest and low-latency pipeline. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-04 | Advanced innovation & monetization | Implement FAST-style scheduled linear channels | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Implement FAST-style scheduled linear channels. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-05 | Advanced innovation & monetization | Implement watch parties with realtime synchronization and moderation | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Implement watch parties with realtime synchronization and moderation. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-06 | Advanced innovation & monetization | Add loyalty/rewards and safe personalization controls | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add loyalty/rewards and safe personalization controls. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-07 | Advanced innovation & monetization | Add multi-tenant white-label OTT capabilities if commercially justified | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add multi-tenant white-label OTT capabilities if commercially justified. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-08 | Advanced innovation & monetization | Provide AI search assistant grounded in licensed catalog | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Provide AI search assistant grounded in licensed catalog. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-09 | Advanced innovation & monetization | Add scene-level discovery and recommendation exploration | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add scene-level discovery and recommendation exploration. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-10 | Advanced innovation & monetization | Add localization-quality translation workflows and assisted dubbing | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add localization-quality translation workflows and assisted dubbing. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-11 | Advanced innovation & monetization | Add 4K HDR/Dolby formats as device/licence support grows | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add 4K HDR/Dolby formats as device/licence support grows. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-12 | Advanced innovation & monetization | Add ad measurement, fraud detection and privacy controls | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Add ad measurement, fraud detection and privacy controls. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.
Q-13 | Advanced innovation & monetization | Introduce advanced creator licensing marketplace and royalties | No | Not started / no evidence found | No | Workstream-level source / documents only | None identified | Not started / no evidence found: Introduce advanced creator licensing marketplace and royalties. Confirm no earlier implementation covers this requirement, then design/build and test. | Confirm no earlier implementation covers this requirement, then design/build and test.

## Workstreams
Section | Workstream | Total | Locally implemented | Partially implemented | Prepared, not executed | Externally blocked | Not started / no evidence found
A | Build, repository & local runtime | 16 | 4 | 4 | 8 | 0 | 0
B | Identity, security & user accounts | 15 | 0 | 7 | 6 | 1 | 1
C | Catalog, metadata, rights & moderation | 15 | 3 | 9 | 0 | 1 | 2
D | Creator upload & media processing | 18 | 6 | 9 | 1 | 0 | 2
E | Netflix-style player & playback | 24 | 15 | 5 | 3 | 0 | 1
F | DRM, entitlement & streaming security | 19 | 3 | 5 | 2 | 1 | 8
G | Subscriptions & international payments | 17 | 3 | 6 | 1 | 2 | 5
H | Search, recommendations & AI | 17 | 5 | 7 | 0 | 0 | 5
I | Analytics & quality of experience | 13 | 4 | 5 | 0 | 0 | 4
J | UI, accessibility & localization | 14 | 5 | 6 | 1 | 0 | 2
K | Creator Studio & administration | 13 | 0 | 6 | 0 | 0 | 7
L | AWS & worldwide distribution | 25 | 4 | 9 | 6 | 2 | 4
M | Mobile, TV & offline viewing | 15 | 0 | 1 | 1 | 1 | 12
N | Privacy, legal & compliance | 15 | 0 | 6 | 1 | 8 | 0
O | Security & engineering quality | 18 | 4 | 7 | 6 | 1 | 0
P | Reliability, performance & recovery | 15 | 1 | 5 | 7 | 0 | 2
Q | Advanced innovation & monetization | 13 | 0 | 0 | 0 | 0 | 13
TOTAL |  | 282 | 57 | 97 | 43 | 17 | 68 | 0

## Read Me
HOW TO INTERPRET REELNEST TASK STATUS
Version | Build 19, 2026-10-22
Basis | Existing source code, historical implementation reports, and Build 19 task register.
Locally implemented | Source or artifact appears to implement the described functionality. Not necessarily deployed or acceptance tested.
Partially implemented | Some supporting behavior is present, but the task has known missing functionality.
Prepared, not executed | Code, scripts or configuration are prepared, but the required live procedure or run has not been verified.
Externally blocked | Needs accounts, provider environments, licensing, external audit, store approval or similar outside action.
Not started / no evidence found | No task-level implementation found in this source/document review. Could change after a deeper audit.
Acceptance | All 282 original checklist acceptance boxes remain unverified; this dashboard is not an approval to launch.
Original 117 screenshot | Its 117 task statistics are an earlier differently scoped audit. Do not extrapolate 17/56/10/19/15 to 282.
Source evidence | Paths are indicative references, not proof that every behavior works end-to-end.
Need to verify | Maven/npm build, Docker, Flyway migrations, Keycloak, Razorpay sandbox, CloudFront/AWS, licensed films, security/legal review.